## DAI Breakdown
Domain​ | Application​ | Source | Client Phase | DAI Phase | DAI Team
Customer Order ​ | Order Flow​ | SAP | Phase 1 | Phase 1 | Week1
Customer Order ​ | Order Flow​ | WMS | Phase 2 | Phase 1 | Week1
Customer Order ​ | Order Flow​ | TMS | Phase 3 | Phase 2
Customer Order ​ | Shipment Performance​ | SAP | Phase 1 | Phase 1 | Week 2
Customer Order ​ | Shipment Performance​ | JDA/O9 | Phase 1 | Phase 1 | Week 3
Customer Order ​ | Forecast Gap Filling​ | SAP | Phase 2 | Phase 2
Customer Order ​ | Forecast Gap Filling​ | JDA/O9 | Phase 2 | Phase 2
Customer Order ​ | Forecast Gap Filling​ | Databricks (Calculations) | Phase 2 | Phase 2
Initiative & Promo Tracker​ | Initiative Management​ | Blueplanner | Phase 2 | Phase 2
Initiative & Promo Tracker​ | Initiative Management​ | Input Tool | Phase 2 | Phase 2
Risk Management ​ | Alert Tracker​ | SAP | Phase 2 (Reports - TMS) | Phase 2
Risk Management ​ | Alert Tracker​ | TMS | Phase 3 (Notification + TMS) | Phase 2
Risk Management ​ | Alert Tracker​ | Azure (Notifications) |  | Phase 2
Risk Management ​ | MIR/LIS​ | SAP | Phase 1 (Low Complexity Calcs) | Phase 2
Risk Management ​ | MIR/LIS​ | JDA/O9 | Phase 2 (All) | Phase 2
Customer Health ​ | Dispute Monitor​ | SAP | Phase 1 (Need to check Tables) | Phase 1 | Week 2
Customer Health ​ | Dispute Monitor​ | High Radius | Phase 2 | Phase 2
Customer Health ​ | Pricing​ | SAP | Phase 1 (Report) | Phase 1 | Week 3
Customer Health ​ | ,Pricing (Simulation)​ | Databricks (Calculations) | Phase 3 (Simulation) | Phase 2
Customer Health ​ | Service​ | SAP | Phase 1 | Phase 1 | Week 3
Customer Health ​ | Service​ | BW4 | Phase 1 | Phase 1 | Week 3
Customer Health ​ | Service​ | High Radius | Phase 1 | Phase 2
Metadata & Data profiling
SSTM
BA with SAP knowledge
DataARch + Modeller : Azure Databrics
Week5 , week 6 - UI vs Data model bridging. Perfomrance SLA etc
Week 5 to Week 8 - SSTM mapping.
2 Azure DB Engineers from Week 5 to Week 8 - Data warehousing
Darch - Offshore , BA onsite
PM , BA -> both Vertical
QA -> 1 Data and Visualization
1 Arch BI / Sr Lead engg Develper
1 PBI Developer

## Revised Requirements
Revised
Latest Priority | Old Priority | Domain | Application | Type | Systems | Flag
P1 | P1 | Customer Order | Order Flow | Report | SAP | Original
P1 | P2 | Customer Order | Order Flow | Report | WMS | Original
P1 | P3 | Customer Order | Order Flow | Report | TMS | New
P1 | P1 | Customer Health | Pricing | Report | SAP | Original
P1 |  | Customer Order | Cut Recovery | Report + Alert | SAP | New
P1 |  | Customer Order | Cut Recovery | Report + Alert | JDA/O9 | New
P1 |  | Customer Health | Customer Scorecard | Report | SAP | New
P1 |  | Customer Health | Customer Scorecard | Report | BW4 | New
P2 | P1 | Customer Order | Shipment Performance | Report | SAP
P2 | P1 | Customer Order | Shipment Performance | Report | JDA/O9
P2 | P2 | Customer Order | Forecast Gap Filling | Report + Calculation | SAP
P2 | P2 | Customer Order | Forecast Gap Filling | Report + Calculation | JDA/O9
P2 | P2 | Customer Order | Forecast Gap Filling | Report + Calculation | Databricks (Calculations)
P2 | P2 | Initiative & Promo Tracker | Initiative Management | Input Tool | Blueplanner
P2 | P2 | Initiative & Promo Tracker | Initiative Management | Input Tool | Input Tool
P2 | P2 | Risk Management | Alert Tracker | Report + Notifications | SAP
P2 | P2 | Risk Management | Alert Tracker | Report + Notifications | TMS
P2 | P3 | Risk Management | Alert Tracker | Report + Notifications | Azure (Notifications)
P2 | P1 | Risk Management | MIR/LIS | Report | SAP
P2 | P2 | Risk Management | MIR/LIS | Report | JDA/O9
P2 | P1 | Customer Health | Dispute Monitor | Report | SAP
P2 | P2 | Customer Health | Dispute Monitor | Report | High Radius
P2 | P1 | Customer Health | Service | Report | SAP
P2 | P2 | Customer Health | Service | Report | BW4
P2 | P2 | Customer Health | Service | Report | High Radius
P2 | P3 | Customer Health | Pricing (Simulation) | Simulation | Databricks (Calculations)

## Assumptions ,ProJect Phases
Phase-1 ( Assumption of # of Tables ) |  | SAP | SAP BW | WMS | JDA/O9 | [7 empty] | Project Phase | Sup-Phase | Scope of Work | Duration | Required Roles | Required Skills | Assumptions
| Customer Order | [11 empty] | Phase-1 | Discovery & Design | Data Profiling - 160 Tables | W1 | Data Arch , BA | DataARch + Modeller : Azure Databrics SAP Knowledge for BA | Number of tables assumption are based on the general understanding of the system. Number of columns per table are assumed to be in the range of 30-40 columns. Assuming to have required Business keys to drive primary keys for joining header/details tables.
| Order Flow | 20 |  | 20 | [10 empty] | Data Modelling for Semantic Layer. Databricks tables as source to Semantic Layer tables as Target | W1-W3 | Data Arch , BA |  | Build STTM document
| Shipment Performance | 20 |  |  | 20 | [9 empty] | Fine tune physical model for UI performance | W4 | Data Arch , BA |  | Collaborate with UI team to finetune the physical data model to address any UI performance.
| Customer Health | [12 empty] | Pilot Phase (20-30 customers) | Choose subset of customers. Build tables and queries, Load data to test the functionality | W5-W6 | Data Arch , BA , 2 Data Engineers |  | Consider 20-30 customer in agreement with customer for testing
| Dispute Monitor | 20 | [12 empty] | Test Functionality using excel dashboards. Prepare test cases | W7-W8 | Data Arch , BA , 2 Data Engineers |  | Once the funcitonalities are tested , will scale in build phase. If any calibration needed on the data model basis output of Pilot testing , extra sprints to be reserved to change the datamodel and retest the functionalities
| Pricing | 20 | [11 empty] | Build Phase | Build Customer Order Flow data - Dev | W9-W10 | Data Arch , BA , 2 Data Engineers |  | Build for order flow will be considered in this sprint.
| Service | 20 | 20 | [11 empty] | Build Customer Order Flow data - UAT & PROD | W11 | Data Arch , BA , 2 Data Engineers |  | The code of order flow to be promoted to UAT , Prod thorugh CI/CD ( Coty team takes care of deployment)
| TOTAL | 100 | 20 | 20 | 20 | 160 | [8 empty] | Build Customer Oder Shipment Performance - Dev | W11-W12 | Data Arch , BA , 2 Data Engineers |  | Build for Customer order shipment performence will be considered in this sprint.
[15 empty] | Build Customer Oder Shipment Performance - UAT & PROD | W13 | Data Arch , BA , 2 Data Engineers |  | The code of shipement performance to be promoted to UAT , Prod thorugh CI/CD ( Coty team takes care of deployment)
[15 empty] | Build Customer Health - Dispute Monitor, Pricing - Dev | W13-W14 | Data Arch , BA , 2 Data Engineers |  | Build for dispute monitor will be considered in this sprint.
Phase-2( Assumption of # of Tables ) |  | SAP | SAP BW | WMS | JDA/O9 | TMS | Databricks (Calculations) | High Radius | Azure Notifications | BluePlanner | Input Tool |  |  |  | Build Customer Health - Dispute Monitor, Pricing - UAT & PROD | W15 | Data Arch , BA , 2 Data Engineers |  | The code of dispute monitor to be promoted to UAT , Prod thorugh CI/CD ( Coty team takes care of deployment)
| Customer Order | [13 empty] | Build Customer Health Service - Dev | W15-W16 | Data Arch , BA , 2 Data Engineers |  | Build for Customer helath service will be considered in this sprint.
| Order Flow |  |  |  |  | 20 | [8 empty] | Build Customer Health Service - UAT & PROD | W17 | Data Arch , BA , 2 Data Engineers |  | The code of dispute monitor to be promoted to UAT , Prod thorugh CI/CD ( Coty team takes care of deployment)
| Forecast Gap Filling | 20 |  |  | 20 |  | 10 | [7 empty] | Tech Debt - Performance optimization - Dev, UAT & PROD | W17-W18 | Data Arch , BA , 2 Data Engineers |  | Extra sprint reserved to address any tech debt
| Customer Health | [11 empty] | Phase-2 | Discovery & Design | Data Profiling - 260 Tables | W11 | Data Arch , BA |  | Number of tables assumption are based on the general understanding of the system. Number of columns per table are assumed to be in the range of 30-40 columns. Assuming to have required Business keys to drive primary keys for joining header/details tables.
| Dispute Monitor | [6 empty] | 20 | [6 empty] | Data Modelling for Semantic Layer. Databricks tables as source to Semantic Layer tables as Target | W12-W13 | Data Arch , BA |  | Build STTM document
| Pricing (Simulation) | [5 empty] | 10 | [7 empty] | Fine tune physical model for UI performance | W14 | Data Arch , BA
| Service | [6 empty] | 20 | [5 empty] | Data Ingestion to Databricks | 2 systems - Build TMS & HighRadius Data ingestion to Databricks Data Lake | W15-W16 | Data Arch , BA , 1 Data Engineers |  | By this team or existing COTY team as per the customer preferred ingestion pattern based on identified connector. (File based or Data pull from application via API)
| Risk Management | [12 empty] | Pilot Phase (20-30 customers) | Choose subset of customers. Build tables and queries, Load data to test the functionality | W17-W18 | Data Arch , BA , 1 Data Engineers |  | Consider 20-30 customer in agreement with customer for testing
| Alert Tracker | 20 |  |  |  | 20 |  |  | 20 | [5 empty] | Test Functionality using excel dashboards. Prepare test cases | W19-W20 | Data Arch , BA , 3 Data Engineers
| MIR/LIS | 20 |  |  | 20 | [8 empty] | Build Phase | Build Risk Management MIR/LIS, Alert Tracker - Dev | W21-W22 | Data Arch , BA , 3 Data Engineers
| Initiative & Promo Tracker | [13 empty] | Build Risk Management MIR/LIS, Alert Tracker - UAT & PROD | W23 | Data Arch , BA , 3 Data Engineers
| Initiative Management | [8 empty] | 20 | 20 |  |  |  | Build Initiative & Promo Tracker Initiative Management - Dev | W23-W24 | Data Arch , BA , 3 Data Engineers |  | Forecast models are assumed to have been developed by COTY team. Does Brillio needs to provide AI/ML model development?
| TOTAL | 60 | 0 | 0 | 40 | 40 | 20 | 40 | 20 | 20 | 20 | 260 |  |  | Build Initiative & Promo Tracker - Initiative Management - UAT & PROD | W25 | Data Arch , BA , 3 Data Engineers
[15 empty] | Build Customer Order Forecast Gap filling - Dev | W25-W26 | Data Arch , BA , 3 Data Engineers
[15 empty] | Build Customer Order Forecast Gap filling - UAT & PROD | W27 | Data Arch , BA , 3 Data Engineers
[11 empty] | 380 |  |  |  | Build Customer Health - Dispute Monitor, Pricing Simulation - Dev | W27-W28 | Data Arch , BA , 2 Data Engineers
[15 empty] | Build Customer Health - Dispute Monitor, Pricing Simulation - UAT & PROD | W29 | Data Arch , BA , 2 Data Engineers
[15 empty] | Build Customer Order Flow, Customer Health Service - Dev | W29-W30 | Data Arch , BA , 2 Data Engineers
[15 empty] | Build Customer Order Flow, Customer Health Service - UAT & PROD | W31 | Data Arch , BA , 2 Data Engineers
[15 empty] | Tech Debt - Performance optimization | W31-W32 | Data Arch , BA , 2 Data Engineers
Phase-1 ( Assumption of # of Tables ) |  | SAP | SAP BW | WMS | JDA/O9 | TMS | [6 empty] | Project Phase | Sup-Phase | Scope of Work | Duration | Required Roles | Required Skills | Assumptions
| Customer Order | [11 empty] | Phase-1 | Discovery & Design | Data Profiling - 20 Tables | W1 | Data Arch , BA | DataARch + Modeller : Azure Databrics SAP Knowledge for BA | Number of tables assumption are based on the general understanding of the system. Number of columns per table are assumed to be in the range of 30-40 columns. Assuming to have required Business keys to drive primary keys for joining header/details tables.
| Order Flow | 20 | [12 empty] | Data Modelling for Semantic Layer. Databricks tables as source to Semantic Layer tables as Target | W1-W3 | Data Arch , BA |  | Build STTM document
[15 empty] | Fine tune physical model for UI performance | W4 | Data Arch , BA |  | Collaborate with UI team to finetune the physical data model to address any UI performance.
| Customer Health | [12 empty] | Pilot Phase (20-30 customers) | Choose subset of customers. Build tables and queries, Load data to test the functionality | W5-W6 | Data Arch , BA , 2 Data Engineers |  | Consider 20-30 customer in agreement with customer for testing
| Pricing | 20 | [12 empty] | Test Functionality using excel dashboards. Prepare test cases | W7-W8 | Data Arch , BA , 2 Data Engineers |  | Once the funcitonalities are tested , will scale in build phase. If any calibration needed on the data model basis output of Pilot testing , extra sprints to be reserved to change the datamodel and retest the functionalities
| Cut Recovery | 20 |  |  | 20 | [9 empty] | Build Customer - Order Flow - SAP,WMS | W11-W12 | Data Arch , BA , 2 Data Engineers |  | Build for Customer order shipment performence will be considered in this sprint.
| Customer Scorecard | 20 | [12 empty] | Build Customer Oder Shipment Performance - UAT & PROD | W13 | Data Arch , BA , 2 Data Engineers |  | The code of shipement performance to be promoted to UAT , Prod thorugh CI/CD ( Coty team takes care of deployment)
| TOTAL | 80 | 0 | 0 | 0 | 80 | [8 empty] | Build Customer - Order Flow - TMS + Pricing | W13-W14 | Data Arch , BA , 2 Data Engineers |  | Build for dispute monitor will be considered in this sprint.
[15 empty] | Build Customer - Order Flow - TMS - UAT & PROD | W15 | Data Arch , BA , 2 Data Engineers |  | The code of dispute monitor to be promoted to UAT , Prod thorugh CI/CD ( Coty team takes care of deployment)
[15 empty] | Build Customer Health Service - Cut Recovery + Scorecard | W15-W16 | Data Arch , BA , 2 Data Engineers |  | Build for Customer helath service will be considered in this sprint.
[15 empty] | Build Customer Health Service - UAT & PROD | W17 | Data Arch , BA , 2 Data Engineers |  | The code of dispute monitor to be promoted to UAT , Prod thorugh CI/CD ( Coty team takes care of deployment)
Build 50 tables on top of existing 80 tables | [7 empty] | Dev, QA, Prod
|  | 20% | 40% | 40% | Effort in Hours |  |  | Total Effort
| Number of Tables | S | M | C | S | M | C | S | M | C
Analysis | 80 | 16 | 32 | 32 | 2 | 4 | 6 | 32 | 128 | 192 | 352 |  | Architect | 492 | 61.5 | 3.075
Design & Data Model | 50 | 10 | 20 | 20 | 2 | 5 | 8 | 20 | 100 | 160 | 280 |  | Data Engg + QA | 836 | 104.5 | 2.6125
Build (DDL & Pipeline to load) | 50 | 10 | 20 | 20 | 4 | 8 | 12 | 40 | 160 | 240 | 440
Test | 50 | 10 | 20 | 20 | 2 | 4 | 6 | 20 | 80 | 120 | 176
TOTAL | 230 | 46 | 92 | 92 | 10 | 21 | 32 | 112 | 468 | 712 | 1292
161.5
53.8333

## DAI-ProjectExec
Practice | DE Phase 1 |  | Discovery & Design |  |  |  | Pilot- (Set of customers) |  |  |  |  | Build + CI/CD
|  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | Total PDs | Total hrs | BR (Euro) | Total
DAI | Data Arch -C2 | 2.5 | [33 empty] | 50 | 450 | 45 | 20250 | bar: Discovery & Design W1 to Build + CI/CD W10
DAI | Business Analyst-B2 | 2.5 | [33 empty] | 50 | 450 | 51 | 22950 | bar: Discovery & Design W1 to Build + CI/CD W10
DAI | Data Engineer-B1 | 2.5 | [33 empty] | 50 | 450 | 35 | 15750 | bar: Pilot- (Set of customers) W5 to Build + CI/CD W14
DAI | Data Engineer-B1 | 3 | [33 empty] | 60 | 540 | 35 | 18900 | bar: Pilot- (Set of customers) W5 to Build + CI/CD W16
DAI | QA Engineer-A1 | 0 | [33 empty] | 0 | 0 | 29 | 0
0
| DE Phase 2 | 0 | Build + CI/CD W11: Discovery & Design; Build + CI/CD W15: Pilot Phase (20-30 customers); Build + CI/CD W19: Build + CI/CD
DAI | Data Arch -C2 | 5.5 | [33 empty] | 110 | 990 | 45 | 44550 | bar: Build + CI/CD W11 to Build + CI/CD W32
DAI | Business Analyst-B2 | 5.5 | [33 empty] | 110 | 990 | 51 | 50490 | bar: Build + CI/CD W11 to Build + CI/CD W32
DAI | Data Engineer-B1 | 4.5 | [33 empty] | 90 | 810 | 35 | 28350 | bar: Build + CI/CD W15 to Build + CI/CD W32
DAI | Data Engineer-B1 | 4 | [33 empty] | 80 | 720 | 35 | 25200 | bar: Build + CI/CD W17 to Build + CI/CD W32
DAI | QA Engineer-A1 | 0 | [33 empty] | 0 | 0 | 29 | 0
| DataScientist-A1 | 1 | [33 empty] | 20 | 180 | 27 | 4860 | bar: Build + CI/CD W29 to Build + CI/CD W32
0
0 | bar: Build + CI/CD W22
| PBI Phase1 | 0 | Discovery & Design W4: Discovery & Design; Build + CI/CD W11: Development & Scale
DAI | BI Architect-C2 | 2 | [33 empty] | 40 | 360 | 43 | 15480 | bar: Discovery & Design W1 to Pilot- (Set of customers) W8
Vertical | Power App Lead (B1) | 0 | [33 empty] | 0 | 0 | 39 | 0
Vertical | Power App Developer (A1) | 0 | [33 empty] | 0 | 0 | 31 | 0
DAI | Power BI Developer-A1 | 2.5 | [33 empty] | 50 | 450 | 24 | 10800 | bar: Pilot- (Set of customers) W7 to Build + CI/CD W16
DAI | Power BI Developer-A1 | 2.5 | [33 empty] | 50 | 450 | 24 | 10800 | bar: Pilot- (Set of customers) W7 to Build + CI/CD W16
DAI | BI QA Engg-A1 | 0 | [33 empty] | 0 | 0 | 24 | 0
0
0
0
| PBI Phase2 | 0 | bar: Build + CI/CD W17 to Build + CI/CD W27
DAI | BI Architect-B1 | 0 | [33 empty] | 0 | 0 | 34 | 0
Vertical | Power App Lead (B1) | 1.75 | [33 empty] | 35 | 315 | 39 | 12285 | bar: Build + CI/CD W17 to Build + CI/CD W23
Vertical | Power App Developer (A1) | 0 | [33 empty] | 0 | 0 | 31 | 0
DAI | Power BI Developer-A1 | 4 | [33 empty] | 80 | 720 | 24 | 17280 | bar: Build + CI/CD W17 to Build + CI/CD W32
DAI | Power BI Developer-A1 | 4 | [33 empty] | 80 | 720 | 24 | 17280 | bar: Build + CI/CD W17 to Build + CI/CD W32
DAI | BI QA Engg-A1 | 0 | [33 empty] | 0 | 0 | 24 | 0
0
| UX | 0
|  | 0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | [10 empty] | Total PDs | Total hrs
Vertical | Design PM (C2) | 0 0: 0.5; 0 W1: 0.25; 0 W2: 0.25; 0 W3: 0.25; 0 W4: 0.25; 0 W5: 0.25; 0 W6: 0.25; 0 W7: 0.25; 0 W8: 0.25 | [10 empty] | 10 | 90 | 48 | 4320
Vertical | Researcher (A2) | 0 0: 0 | [10 empty] | 0 | 0 | 22 | 0
Vertical | UX Lead (B2) | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [17 empty] | 80 | 720 | 30 | 21600
Vertical | UX Designer (A1) | 0 0: 5.5; 0 W11: 1; 0 W12: 1; 0 W13: 1; 0 W14: 1; 0 W15: 1; 0 W16: 1; 0 W17: 1; 0 W18: 1; 0 W19: 1; 0 W20: 1; 0 W21: 1; 0 W22: 1; 0 W23: 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 110 | 990 | 30 | 29700
Vertical | UX Designer (A2) | 0 0: 0 | [10 empty] | 0 | 0 | 24 | 0
0
| PM | 0 0: 0
|  | 0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 |  | Total PDs | Total hrs
DAI | PM/Scrum Master (C2) | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 160 | 1440 | 44 | 63360
Vertical | Design Director (D2-US) | 0 0: 0 |  | 0 | 0 | 286 | 0
DAI | Delivery Manager-D3 | 0.8 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 16 | 144 | 50 | 7200
|  | 0 0: 0 |  | 0 | 0 |  | 0
[36 empty] | 1331 | 11979 |  | 441405
| DE Phase 3 | 0 W11: Discovery & Design; 0 W15: Pilot Phase (20-30 customers); 0 W19: Build + CI/CD
DAI | Data Arch -C2 | [34 empty] | 15 | 135 | 45 | 6075 | bar: 0 W30 to 0 W32
DAI | Business Analyst-B2 | [34 empty] | 15 | 135 | 51 | 6885 | bar: 0 W30 to 0 W32
DAI | Data Engineer-B1 | [34 empty] | 15 | 135 | 35 | 4725 | bar: 0 W30 to 0 W32
DAI | Data Engineer-B1 | [34 empty] | 15 | 135 | 35 | 4725 | bar: 0 W30 to 0 W32
DAI | QA Engineer-A1 | [34 empty] | 15 | 135 | 29 | 3915 | bar: 0 W30 to 0 W32
| DataScientist-A1 | [34 empty] | 15 | 135 | 27 | 3645 | bar: 0 W30 to 0 W32
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on J37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on J45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived

## PBI Effort Calculation
Overall Estimation
In Hrs
Overall Efforts | 1310 |  | 163.75
C-360 Power BI Development |  |  | C-360 Power App Development |  |  | 5
Activites | In Hours | In Days | Activites | In Hours | In Days
Discovery | 80 | 10 | Discovery | 32 | 4
Development | 563 | 62 | Screen Development | 76 | 9.5
Analysis | 40 | 5 | Data Connection Setup | 60 | 7.5 | 3-4 flows
Unit Testing | 50 | 6 | Unit Testing | 40 | 5
UAT/QA Support | 80 | 10 | UAT/QA Support | 40 | 5 | Writeback to Databricks
Deployment | 16 | 2 | Deployment | 16 | 2
Total Efforts | 829 | 95 | Total Efforts | 264 | 33
C-360 Power Automate Flows Development
Activites | In Hours | In Days
Discovery | 24 | 3
Sharepoint Site and Schema setup for intrim writeback to DB | 32 | 4
Setup ADF Job for writeback | 40 | 5
Alerts | 25 | 3.125
Writeback Flows | 40 | 5
Unit Testing | 32 | 4
Azure Function Setup | 8 | 1
Deployment | 16 | 2
Total Efforts | 217 | 27.125

## PBI Deliverables
Total Hours | 563
C360 Dashboard |  | In Hours | C360 Dashboard |  | Activities
Development Efforts in Hours |  |  | Efforts in Object Count |  | Metrics Calculation
Data Modeling | Simple | 0 | Data Modeling | Simple | 0
| Medium | 32 |  | Medium | 2
| Complex | 64 |  | Complex | 2
| Simple | 0 |  | Simple | 0
UI/UX | Medium | 16 | UI/UX | Medium | 2
| Complex | 64 |  | Complex | 2
Metrics Calculation | Simple | 25 | Metrics Calculation | Simple | 25
| Medium | 50 |  | Medium | 25
| Complex | 136 |  | Complex | 34
Dashboard Development | Simple | 0 | Dashboard Development | Simple | 0
| Medium | 48 |  | Medium | 2
| Complex | 128 |  | Complex | 2
563
0

## PBI Estimation Hours
Activites | Effort - Hours
| Simple | Medium | Complex
Requirement Gathering | 16 | 24 | 40
Design | 8 | 16 | 32
Data Modeling | 8 | 16 | 32
Metrics Calculation | 1 | 2 | 4
Dashboard Development | 8 | 24 | 64
Security Implementation | 8 | 16 | 32
Unit Testing | 8 | 16 | 16
Deployment | 4 | 4 | 4
Total | 45 | 86 | 160

## PBI Effort (hidden)
Devendra
|  | DISCOVERY | UX | Implementation | [5 empty] | Testing,Deployment,Documentation
Complexity | # of Screens | Discovery & Design | UX Effort | PowerApps UI Design | Power Automate - Email Notifications | Data Integration | Power BI | Write Operation to Data Source | UAT Issues and Enhancement | Unit Testing | Documentation | Prod Deployment
Simple | 8 | 7 | 3 | 8 | 3 | 3 | 0 | 0 | 3 | 12 | 5 | 2 | 46
Medium | 1 | 0 | 0 | 2 | 2 | 0 | 5 | 3 | 2 | 0 | 0 | 0 | 14
Complex | 15 | 0 | 0 | 45 | 5 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 62
|  | 7 | 3 | 93 | [5 empty] | 19
[6 empty] | Total Efforts ( In Days) | 122 | 24.4

## DAI Monthly RL (hidden)
Phase 1
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9
Data Arch | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
Business Analyst | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
Data Engineer | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0
Data Engineer-Onshore | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
QA Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase 2
Data Arch | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1
Business Analyst | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1
Data Engineer | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Data Engineer-Onshore | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
PBI Loading
BI Architect | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Business Analyst | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Power App Developer | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Power App Developer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Power BI Developer | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0

## DAI Loading (hidden)
Phase 1 | Discovery & Design |  |  |  | Pilot- Development (Set of customers) |  |  |  | Full Fledged Development |  |  |  | Production Deployment / Support
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
| BA,Arch | BA,Arch | BA,Arch | BA,Arch | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE
Data Arch | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Business Analyst | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Data Engineer | bar: Pilot- Development (Set of customers) W5 to Production Deployment / Support W16
Data Engineer-Onshore | bar: Pilot- Development (Set of customers) W5 to Production Deployment / Support W16
QA Engineer | Pilot- Development (Set of customers) W6: 1; Pilot- Development (Set of customers) W7: 1; Pilot- Development (Set of customers) W8: 1; Full Fledged Development W9: 0.5; Full Fledged Development W10: 0.5; Full Fledged Development W11: 0.5; Full Fledged Development W12: 0.5; Production Deployment / Support W13: 0.5; Production Deployment / Support W14: 0.5; Production Deployment / Support W15: 0.5; Production Deployment / Support W16: 0.5
Phase 2 | Full Fledged Development W11: Discovery & Design; Production Deployment / Support W15: Pilot- Development (Set of customers); Production Deployment / Support W19: SIT ( DAI+UI); Production Deployment / Support W21: Code Promotion + UAT; Production Deployment / Support W25: Production Deployment / Support
[11 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
[11 empty] | BA,Arch,1 DE | BA,Arch,1 DE | BA,Arch,1 DE | BA,Arch,1 DE | BA,Arch,1 DE | BA,Arch,1 DE | BA,Arch,3 DE | BA,Arch,3 DE | BA,Arch,3 DE | BA,Arch,3 DE | BA,Arch,3 DE | BA,Arch,3 DE | BA,Arch,3 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE | BA,Arch,2 DE
Data Arch | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Business Analyst | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Data Engineer | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
Data Engineer-Onshore | bar: Discovery & Design W1 to Production Deployment / Support W16
QA Engineer | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PBI Loading | [7 empty] | Discovery & Design |  |  | Pilot- Development (Set of customers) W5: Development; Code Promotion + UAT W11: Code Promotion + UAT; Production Deployment / Support W15: Production Deployment / Support
[8 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23
[8 empty] | BA,Arch | BA,Arch | BA,Arch | BA,Arch | BA,Arch | BA,Arch | BA,Arch | BA,Arch,2 PD | BA,Arch,2PD | BA,Arch,2 PD | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI | BA,Arch,2 PD+1PBI
BI Architect | bar: Discovery & Design W1 to Production Deployment / Support W23
Business Analyst | bar: Discovery & Design W1 to Production Deployment / Support W23
Power App Lead (B1) | bar: Discovery & Design W5 to Production Deployment / Support W23
Power App Developer (A1) | bar: Development W8 to Production Deployment / Support W23
Power BI Developer | [16 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[10 empty] | M1 |  |  |  | M2 |  |  |  | M3
PBI Phase1 | [7 empty] | Discovery & Design W1: Discovery & Design; Development W8: Development & Scale
[10 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | Total PDs | Total hrs
BI Architect-C2 | [9 empty] | W1: 1; W2: 1; W3: 1; W4: 1; W5: 1; Development & Scale W6: 1; Development & Scale W7: 1; Development & Scale W8: 0.5; Development & Scale W9: 0.5; Development & Scale W10: 0.5; Development & Scale W11: 0.5; Development & Scale W12: 0.5 | 47.5 | 427.5 | 43 | 18382.5
Power App Lead (B1) | [9 empty] | W3: 1; W4: 1; W5: 1; Development & Scale W6: 1; Development & Scale W7: 1; Development & Scale W8: 0.5; Development & Scale W9: 0.5; Development & Scale W10: 0.5; Development & Scale W11: 0.5; Development & Scale W12: 0.5 | 37.5 | 337.5 | 39 | 13162.5
Power App Developer (A1) | [9 empty] | W4: 1; W5: 1; Development & Scale W6: 1; Development & Scale W7: 1; Development & Scale W8: 1; Development & Scale W9: 1; Development & Scale W10: 0.5; Development & Scale W11: 0.5; Development & Scale W12: 0.5 | 37.5 | 337.5 | 31 | 10462.5
Power BI Developer-A1 | [30 empty] | 35 | 315 | 24 | 7560 | bar: Development & Scale W6 to Development & Scale W12
Power BI Developer-A1 | [9 empty] | Development & Scale W6: 1; Development & Scale W7: 1; Development & Scale W8: 1; Development & Scale W9: 1; Development & Scale W10: 0.5; Development & Scale W11: 0.5; Development & Scale W12: 0.5; Development & Scale W13: 0.375 | 29.375 | 264.375 | 24 | 6345
BI QA Engg-A1 | [30 empty] | 35 | 315 | 24 | 7560 | bar: Development & Scale W6 to Development & Scale W12
[22 empty] | M3 |  |  |  | M3
PBI Phase2 | bar: Development & Scale W8 to Development & Scale W18
[17 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | Total PDs | Total hrs
BI Architect-B1 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 37.5 | 337.5 | 34 | 11475
Power App Lead (B1) | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 37.5 | 337.5 | 39 | 13162.5
Power App Developer (A1) | [18 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 52.5 | 472.5 | 31 | 14647.5
Power BI Developer-A1 | [30 empty] | 45 | 405 | 24 | 9720 | bar: W6 to W14
Power BI Developer-A1 | [18 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 52.5 | 472.5 | 24 | 11340
BI QA Engg-A1 | [30 empty] | 45 | 405 | 24 | 9720 | bar: W6 to W14
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on O22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on O34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on O45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived

## DAI-ProjectExec (3) (hidden)
Practice | DE Phase 1 | Discovery & Design |  |  |  | Pilot- (Set of customers) |  |  |  |  | Build + CI/CD
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | Total PDs | Total hrs | BR (Euro) | Total
DAI | Data Arch -C2 | [33 empty] | 50 | 450 | 45 | 20250 | bar: Discovery & Design W1 to Build + CI/CD W10
DAI | Business Analyst-B2 | [33 empty] | 50 | 450 | 51 | 22950 | bar: Discovery & Design W1 to Build + CI/CD W10
DAI | Data Engineer-B1 | [33 empty] | 60 | 540 | 35 | 18900 | bar: Pilot- (Set of customers) W5 to Build + CI/CD W16
DAI | Data Engineer-B1 | [33 empty] | 60 | 540 | 35 | 18900 | bar: Pilot- (Set of customers) W5 to Build + CI/CD W16
DAI | QA Engineer-A1 | [33 empty] | 40 | 360 | 29 | 10440 | bar: Pilot- (Set of customers) W9 to Build + CI/CD W16
| DE Phase 2 | Build + CI/CD W11: Discovery & Design; Build + CI/CD W15: Pilot Phase (20-30 customers); Build + CI/CD W19: Build + CI/CD
[12 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 |  | Total PDs | Total hrs
DAI | Data Arch -C2 | [33 empty] | 110 | 990 | 45 | 44550 | bar: Discovery & Design W1 to Build + CI/CD W22
DAI | Business Analyst-B2 | [33 empty] | 110 | 990 | 51 | 50490 | bar: Discovery & Design W1 to Build + CI/CD W22
DAI | Data Engineer-B1 | [33 empty] | 90 | 810 | 35 | 28350 | bar: Pilot Phase (20-30 customers) W5 to Build + CI/CD W22
DAI | Data Engineer-B1 | [33 empty] | 80 | 720 | 35 | 25200 | bar: Pilot Phase (20-30 customers) W7 to Build + CI/CD W22
DAI | QA Engineer-A1 | [33 empty] | 80 | 720 | 29 | 20880 | bar: Pilot Phase (20-30 customers) W7 to Build + CI/CD W22
| DataScientist-A1 | [33 empty] | 20 | 180 | 27 | 4860 | bar: Build + CI/CD W19 to Build + CI/CD W22
| PBI Phase1 | [7 empty] | Discovery & Design |  |  | Pilot Phase (20-30 customers) W5: Development & Scale
[10 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 |  |  |  |  | Total PDs | Total hrs
DAI | BI Architect-C2 | [6 empty] | 1 | 1 | W1: 1; W2: 1; W3: 1; W4: 1; W5: 1; W6: 0.25; Development & Scale W7: 0.25; Development & Scale W8: 0.25; Development & Scale W9: 0.25; Development & Scale W10: 0.25 |  |  |  |  | 41.25 | 371.25 | 43 | 15963.75
Vertical | Power App Lead (B1) | [33 empty] | 40 | 360 | 39 | 14040 | bar: W3 to Development & Scale W10
Vertical | Power App Developer (A1) | [33 empty] | 0 | 0 | 31 | 0
DAI | Power BI Developer-A1 | [33 empty] | 40 | 360 | 24 | 8640 | bar: W3 to Development & Scale W10
DAI | Power BI Developer-A1 | [33 empty] | 40 | 360 | 24 | 8640 | bar: W3 to Development & Scale W10
DAI | BI QA Engg-A1 | [33 empty] | 0 | 0 | 24 | 0
PBI Phase2 | bar: Development & Scale W9 to Development & Scale W19
[20 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 |  | Total PDs | Total hrs
DAI | BI Architect-B1 | [18 empty] | 1 | 1 | 1 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | [5 empty] | 31.25 | 281.25 | 34 | 9562.5
Vertical | Power App Lead (B1) | [33 empty] | 60 | 540 | 39 | 21060 | bar: W3 to W14
Vertical | Power App Developer (A1) | [33 empty] | 0 | 0 | 31 | 0
DAI | Power BI Developer-A1 | [33 empty] | 60 | 540 | 24 | 12960 | bar: W3 to W14
DAI | Power BI Developer-A1 | [33 empty] | 0 | 0 | 24 | 0
DAI | BI QA Engg-A1 | [33 empty] | 0 | 0 | 24 | 0
UX
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | [10 empty] | Total PDs | Total hrs
Vertical | Design PM (C2) | W1: 0.25; W2: 0.25; W3: 0.25; W4: 0.25; W5: 0.25; W6: 0.25; W7: 0.25; W8: 0.25; W9: 0.25; W10: 0.25; W11: 0.25; W12: 0.25 | [10 empty] | 15 | 135 | 48 | 6480
Vertical | Researcher (A2) | [33 empty] | 20 | 180 | 22 | 3960 | bar: W1 to W4
Vertical | UX Lead (B2) | W1: 0.5; W2: 0.5; W3: 0.5; W4: 0.5; W5: 0.5; W6: 0.5; W7: 0.5; W8: 0.5; W9: 0.5; W10: 0.5 | [10 empty] | 25 | 225 | 30 | 6750
Vertical | UX Designer (A1) | [33 empty] | 60 | 540 | 30 | 16200 | bar: W1 to W12
Vertical | UX Designer (A2) | [33 empty] | 70 | 630 | 24 | 15120 | bar: W3 to W16
PM
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 |  | Total PDs | Total hrs
DAI | PM/Scrum Master (C2) | [33 empty] | 160 | 1440 | 44 | 63360 | bar: W1 to W32
Vertical | Design Director (D2-US) | W1: 0.1; W2: 0.1; W3: 0.1; W4: 0.1; W5: 0.05; W6: 0.05; W7: 0.05; W8: 0.05; W9: 0.03; W10: 0.03; W11: 0.03; W12: 0.03 |  | 3.6 | 32.4 | 286 | 9266.4
DAI | Delivery Manager-D3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 16 | 144 | 50 | 7200
[35 empty] | 0 | 0 |  | 0
[35 empty] | 1432.1 | 12888.9 |  | 484972.65 | Euro
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on O20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on P31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on I48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived

## DAI-ProjectExec (2) (hidden)
Practice | DE Phase 1 | Discovery & Design |  |  |  | Pilot- (Set of customers) |  |  |  |  | Build + CI/CD
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | Total PDs | Total hrs | BR (Euro) | Total
DAI | Data Arch -C2 | [33 empty] | 50 | 450 | 45 | 20250 | bar: Discovery & Design W1 to Build + CI/CD W10
DAI | Business Analyst-B2 | [33 empty] | 50 | 450 | 51 | 22950 | bar: Discovery & Design W1 to Build + CI/CD W10
DAI | Data Engineer-B1 | [33 empty] | 60 | 540 | 35 | 18900 | bar: Pilot- (Set of customers) W5 to Build + CI/CD W16
DAI | Data Engineer-B1 | [33 empty] | 60 | 540 | 35 | 18900 | bar: Pilot- (Set of customers) W5 to Build + CI/CD W16
DAI | QA Engineer-A1 | [33 empty] | 40 | 360 | 29 | 10440 | bar: Pilot- (Set of customers) W9 to Build + CI/CD W16
| DE Phase 2 | Build + CI/CD W11: Discovery & Design; Build + CI/CD W15: Pilot Phase (20-30 customers); Build + CI/CD W19: Build + CI/CD
[12 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 |  | Total PDs | Total hrs
DAI | Data Arch -C2 | [33 empty] | 110 | 990 | 45 | 44550 | bar: Discovery & Design W1 to Build + CI/CD W22
DAI | Business Analyst-B2 | [33 empty] | 110 | 990 | 51 | 50490 | bar: Discovery & Design W1 to Build + CI/CD W22
DAI | Data Engineer-B1 | [14 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 |  | 140 | 1260 | 35 | 44100
DAI | Data Engineer-B1 | [33 empty] | 80 | 720 | 35 | 25200 | bar: Pilot Phase (20-30 customers) W7 to Build + CI/CD W22
DAI | QA Engineer-A1 | [33 empty] | 80 | 720 | 29 | 20880 | bar: Pilot Phase (20-30 customers) W7 to Build + CI/CD W22
| DataScientist-A1 | [33 empty] | 30 | 270 | 27 | 7290 | bar: Build + CI/CD W16 to Build + CI/CD W21
| PBI Phase1 | [7 empty] | Discovery & Design |  |  | Pilot Phase (20-30 customers) W5: Development & Scale
[10 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 |  |  |  |  | Total PDs | Total hrs
DAI | BI Architect-C2 | [8 empty] | W1: 1; W2: 1; W3: 1; W4: 1; W5: 1; W6: 1; Development & Scale W7: 1; Development & Scale W8: 0.5; Development & Scale W9: 0.5; Development & Scale W10: 0.5; Development & Scale W11: 0.5; Development & Scale W12: 0.5 |  |  |  |  | 47.5 | 427.5 | 43 | 18382.5
Vertical | Power App Lead (B1) | [8 empty] | W3: 1; W4: 1; W5: 1; W6: 1; Development & Scale W7: 1; Development & Scale W8: 0.5; Development & Scale W9: 0.5; Development & Scale W10: 0.5; Development & Scale W11: 0.5; Development & Scale W12: 0.5 |  |  |  |  | 37.5 | 337.5 | 39 | 13162.5
Vertical | Power App Developer (A1) | [8 empty] | W4: 1; W5: 1; W6: 1; Development & Scale W7: 1; Development & Scale W8: 1; Development & Scale W9: 1; Development & Scale W10: 0.5; Development & Scale W11: 0.5; Development & Scale W12: 0.5 |  |  |  |  | 37.5 | 337.5 | 31 | 10462.5
DAI | Power BI Developer-A1 | [33 empty] | 35 | 315 | 24 | 7560 | bar: W6 to Development & Scale W12
DAI | Power BI Developer-A1 | [8 empty] | W6: 1; Development & Scale W7: 1; Development & Scale W8: 1; Development & Scale W9: 1; Development & Scale W10: 0.5; Development & Scale W11: 0.5; Development & Scale W12: 0.5; Development & Scale W13: 0.375 |  |  |  |  | 29.375 | 264.375 | 24 | 6345
DAI | BI QA Engg-A1 | [33 empty] | 35 | 315 | 24 | 7560 | bar: Development & Scale W7 to Development & Scale W13
PBI Phase2 | bar: Development & Scale W9 to Development & Scale W19
[17 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 |  |  |  |  | Total PDs | Total hrs
DAI | BI Architect-B1 | [15 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | [8 empty] | 37.5 | 337.5 | 34 | 11475
Vertical | Power App Lead (B1) | [15 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | [8 empty] | 37.5 | 337.5 | 39 | 13162.5
Vertical | Power App Developer (A1) | [17 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 52.5 | 472.5 | 31 | 14647.5
DAI | Power BI Developer-A1 | [33 empty] | 45 | 405 | 24 | 9720 | bar: W6 to W14
DAI | Power BI Developer-A1 | [17 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 52.5 | 472.5 | 24 | 11340
DAI | BI QA Engg-A1 | [33 empty] | 45 | 405 | 24 | 9720 | bar: W6 to W14
UX
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | [10 empty] | Total PDs | Total hrs
Vertical | Design PM (C2) | W1: 0.25; W2: 0.25; W3: 0.25; W4: 0.25; W5: 0.25; W6: 0.25; W7: 0.25; W8: 0.25; W9: 0.25; W10: 0.25; W11: 0.25; W12: 0.25 | [10 empty] | 15 | 135 | 48 | 6480
Vertical | Researcher (A2) | [33 empty] | 20 | 180 | 22 | 3960 | bar: W1 to W4
Vertical | UX Lead (B2) | W1: 0.5; W2: 0.5; W3: 0.5; W4: 0.5; W5: 0.5; W6: 0.5; W7: 0.5; W8: 0.5; W9: 0.5; W10: 0.5 | [10 empty] | 25 | 225 | 30 | 6750
Vertical | UX Designer (A1) | [33 empty] | 60 | 540 | 30 | 16200 | bar: W1 to W12
Vertical | UX Designer (A2) | [33 empty] | 70 | 630 | 24 | 15120 | bar: W3 to W16
PM
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 |  | Total PDs | Total hrs
DAI | PM/Scrum Master (C2) | [33 empty] | 160 | 1440 | 44 | 63360 | bar: W1 to W32
Vertical | Design Director (D2-US) | W1: 0.1; W2: 0.1; W3: 0.1; W4: 0.1; W5: 0.05; W6: 0.05; W7: 0.05; W8: 0.05; W9: 0.03; W10: 0.03; W11: 0.03; W12: 0.03 |  | 3.6 | 32.4 | 286 | 9266.4
DAI | Delivery Manager-D3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 16 | 144 | 50 | 7200
[35 empty] | 0 | 0 |  | 0
[35 empty] | 1671.475 | 15043.275 |  | 545823.9 | Euro
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on O20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on P31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived
Note on I48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recalibrate the data model if all the KPIs are being achieved , all status are achived

## Old -Assumptions (hidden)
ld -
The data from Sources to Datalake will be taken care by Coty team.
The presentation later will be built in databricks
Coty team to take care of whole Infrastructure needs for the project like - Databricks access , git access , CI/CD deployments etc
Phase 1 | Activites and project phases for Phase 1 as below
Discovery & Design
Description | To assess the Databricks tables of the prioritized source systems, do discovery of the datasets essential for Cust App, Cataloging the datasets, prepare STTM.
Assumptions | In phase 1 considered Applications - Sources as per the DAI Breakdownsheet
Assumption | We assume 15 tables per each source system for SAP,WMS,JDA/O9,BW4 under phase 1 for Discovery and Design
Assumption | Source to Target Mapping .Transformations to be perfomed based on STTM document.
Assumption | In Phase 1- For the applications - Order FLow ,Shipment Performance​,Dispute Monitor​,Pricing​,Service​ , to consider to build 2 datasets/tables per application for Customer APP consumption (in this case 10 datasets)
Activity | Discovery & Design Phase would include data profiling , data modelling of the datasets identified as part of Phase 1
Activity | Regular interactions with UI team inorder to finalize the consumption layer structure This is to determine the logic that can stay in semantic layer vs app layer
Activity | Week 4 to Week 6 - To have interactions with UI team to bridge on the data model that was prepared during Discover & Desing phase and define Performance SLA with UI team
Pilot- Development (Set of customers)
Description | To develop the prototype and showcase the initial functionalities
Assumptions | To consider top 20 customers to perform the testing encompassing all the order status for unit testing
ACtivity | Recalibrate the data model to ensure all KPIs are being achieved , all the order status are achived in Week 7,8
SIT ( DAI+UI)
Description | In system integration testing phase , E2E testing will be conducted , where the user queries the data from Customer app , retrieves the data from presentation layer and displayed back to the UI.
Assumptions | To consider top 20 customers to perform the testing encompassing all the order status for SIT Testing
??? | Where to call out full fledged testing and development where to consider
Code Promotion + UAT
Assumptions | CI/CD pipeline to be developed by the COTY devops team.
Assumptions | Coty Devops team promote the code to UAT through CI/CD
Activity | Coty team to perform UAT , Brillio team to support addressing the defects
Production Deployment / Support
Assumptions | Coty Devops team promote the code to Prod through CI/CD
Activity | Coty tema to validate the prod data , Brillio team to support addressing the defects